## 416
Task | Short Description | Contributor(s) | Status | Date
PDM to PCM | Converts each 1-bit 3.072 MHz PDM signal from the microphones to a 16-bit 48kHz or 192kHz PCM audio signal | Nate | Done | Last week
Time Difference of Arrival | Proof of concept block that determines potential locations in a 2-by-2 quadrant of possible locations | Sandeep | Done | This week
LVMC Beamforming | Creating a covariance matrix and converting the values into possible displayable locations | Kailan, Sandeep, David, Srivibhav, Nate | Done | This week
Cross Covariance Calculation | Calculate the cross covariance matrix of the microphone data | Kailan | Done | Last week
LCMV Weight Calculation | Module to calculate the LCMV output from the CC matrix and saved LCMV weights | Kailan | In Progress | This week
PL to PS Communication | Sending data from PL to PS to eventually use for locations -> heatmap display path (HLS lightweight bridge) | David, Sandeep | Done | Last week
Bandpass Filtering | Select between several pre-determined FIR bandpass filters for analyzing a specific frequency window. FIR filters also compsensate for CIC filter passband droop and intrinsic frequency response of microphones | Nate, Sri | Done | This week
Testing output of Microphones | Checking the output of the microphones gives reasonable recording from inducing a frequency tone | David, Nate, Srivibhav | Done | This week
Integration 2 | Processed PCM mic audio data from PL to PS, output to Linux | Nate, Sri, David | Done | Last week
Integration 3 | TDOA proof of concept | Sandeep | In Progress | This week
Integration 4 | Initial implementation of LVMC beamforming | Kailan | Not Started | Next week
Sound Localization | Save the LCMV weights for each position on 3x3 grid | Kailan | Not Started | Next week
Heatmap Calculation | Calculate heatmap from based on what is received from PL side | Kailan | In Progress | This week

## 49
Task | Short Description | Contributor(s) | Status | Date
Microphone PCB | Design and assembly of 3 separate PCB boards in Altium. Boards use 3 styles of microphone arrays and allow for interfacing mic data with FPGA | Nate | Done | Previous weeks
Microphone Clock Generation | Senses voltage on PCB through on board ADC and starts an FSM detecting mode requested to generate desired clock (Sleep, Standard, Ultrasonic). | Srivibhav, Kailan | Done | Previous weeks
PDM to PCM | Converts each 1-bit 3.072 MHz PDM signal from the microphones to a 16-bit 48kHz or 192kHz PCM audio signal | Nate | Done | This week
Linux Installation onto FPGA | Installation of Linux image and getting FPGA to load it | David, Kailan | Done | Previous weeks
Linux Setup | Connecting FPGA to network and downloading required packages | David, Kailan | Done | Previous weeks
Heatmap Display Overlay | Setup computer vision to allow displaying over a USB camera | Kailan | Done | Previous weeks
Time Difference of Arrival | Proof of concept block that determines potential locations in a 2-by-2 quadrant of possible locations | Sandeep | In Progress | This week
LVMC Beamforming | Creating a covariance matrix and converting the values into possible displayable locations | Kailan, Sandeep, David, Srivibhav, Nate | In Progress | This week
Cross Covariance Calculation | Calculate the cross covariance matrix of the microphone data | Kailan | Done | This week
LCMV Calculation | Module to calculate the LCMV output from the CC matrix and saved LCMV weights | Kailan | In Progress | This week
PL to PS Communication | Sending data from PL to PS to eventually use for locations -> heatmap display path (HLS lightweight bridge) | David, Sandeep | Done | Previous weeks
Bandpass Filtering | Select between several pre-determined FIR bandpass filters for analyzing a specific frequency window. FIR filters also compsensate for CIC filter passband droop and intrinsic frequency response of microphones | Nate | In Progress | This week
Creating Spreadsheet | Spreadsheet to track progress of project | Kailan, Sandeep, Nate, Srivibhav | Done
Testing output of Microphones | Checking the output of the microphones gives reasonable recording from inducing a frequency tone | David, Nate, Srivibhav | In Progress | This week
Integration 1 | Basic Mic Output (PDM from PCB - Oscilliscope) | Nate, Sri, David | Done | Previous weeks
Integration 2 | Processed PCM mic audio data from PL to PS, output to Linux | Nate, Sri, David | Done | This week
Integration 3 | TDOA proof of concept | Sandeep | Not Started
Integration 4 | Initial implementation of LVMC beamforming | Kailan | Not Started
Sound Localization | Save the LCMV weights for each position on 3x3 grid | Kailan | Not Started
Heatmap Calculation | Calculate heatmap from LCMV matrix calculated on PL | Kailan | Not Started